## Backlog
ID | Type | Title | Parent | Priority | Estimate | Tags | Acceptance criteria
work-item-1 | Epic | Tutorial Safety Incident Reporting delivery |  | 1 |  | agentic-sdlc
work-item-2 | Feature | Plan Proposal — Tutorial Safety Incident Reporting | Tutorial Safety Incident Reporting delivery | 1 |  | agentic-sdlc
work-item-3 | User Story | A site worker to submit an incident report quickly. | Plan Proposal — Tutorial Safety Incident Reporting | 2 | 5 | agentic-sdlc | Given the approved requirements for "A site worker to submit an incident report quickly.", when a business user completes the flow, then the outcome matches the behaviour described in Planning Agent output . The UI screen implementing this story matches the approved UX mockups in layout, labelling, and navigation. The API endpoints this story depends on are documented in the OpenAPI document and return the documented status codes, including validation failures. Invalid or missing input is rejected at the API with a clear message; no unhandled exception reaches the user. Automated tests cover the happy path and at least one failure path, and the CI pipeline passes. The change is deployed to Dev and verified by the deployment smoke test.
work-item-4 | Task | Design: A site worker to submit an incident report quickly. | A site worker to submit an incident report quickly. | 2 | 4 | agentic-sdlc
work-item-5 | Task | Implement: A site worker to submit an incident report quickly. | A site worker to submit an incident report quickly. | 1 | 12 | agentic-sdlc
work-item-6 | Task | Test: A site worker to submit an incident report quickly. | A site worker to submit an incident report quickly. | 2 | 6 | agentic-sdlc
work-item-7 | User Story | A safety lead to review, triage, and issue notifications. | Plan Proposal — Tutorial Safety Incident Reporting | 2 | 5 | agentic-sdlc | Given the approved requirements for "A safety lead to review, triage, and issue notifications.", when a administrator completes the flow, then the outcome matches the behaviour described in Planning Agent output . The UI screen implementing this story matches the approved UX mockups in layout, labelling, and navigation. The API endpoints this story depends on are documented in the OpenAPI document and return the documented status codes, including validation failures. Invalid or missing input is rejected at the API with a clear message; no unhandled exception reaches the user. Automated tests cover the happy path and at least one failure path, and the CI pipeline passes. The change is deployed to Dev and verified by the deployment smoke test.
work-item-8 | Task | Design: A safety lead to review, triage, and issue notifications. | A safety lead to review, triage, and issue notifications. | 2 | 4 | agentic-sdlc
work-item-9 | Task | Implement: A safety lead to review, triage, and issue notifications. | A safety lead to review, triage, and issue notifications. | 1 | 12 | agentic-sdlc
work-item-10 | Task | Test: A safety lead to review, triage, and issue notifications. | A safety lead to review, triage, and issue notifications. | 2 | 6 | agentic-sdlc
work-item-11 | Feature | 1. Evidence and current state | Tutorial Safety Incident Reporting delivery | 1 |  | agentic-sdlc
work-item-12 | User Story | Assigned users to manage corrective actions to verified completion. | 1. Evidence and current state | 2 | 5 | agentic-sdlc | Given the approved requirements for "Assigned users to manage corrective actions to verified completion.", when a reviewer completes the flow, then the outcome matches the behaviour described in Planning Agent output . The UI screen implementing this story matches the approved UX mockups in layout, labelling, and navigation. The API endpoints this story depends on are documented in the OpenAPI document and return the documented status codes, including validation failures. Invalid or missing input is rejected at the API with a clear message; no unhandled exception reaches the user. Automated tests cover the happy path and at least one failure path, and the CI pipeline passes. The change is deployed to Dev and verified by the deployment smoke test.
work-item-13 | Task | Design: Assigned users to manage corrective actions to verified completion. | Assigned users to manage corrective actions to verified completion. | 2 | 4 | agentic-sdlc
work-item-14 | Task | Implement: Assigned users to manage corrective actions to verified completion. | Assigned users to manage corrective actions to verified completion. | 1 | 12 | agentic-sdlc
work-item-15 | Task | Test: Assigned users to manage corrective actions to verified completion. | Assigned users to manage corrective actions to verified completion. | 2 | 6 | agentic-sdlc
work-item-16 | User Story | A safety lead to complete the investigation and close it into a durable reporting record. | 1. Evidence and current state | 2 | 5 | agentic-sdlc | Given the approved requirements for "A safety lead to complete the investigation and close it into a durable reporting record.", when a operator completes the flow, then the outcome matches the behaviour described in Planning Agent output . The UI screen implementing this story matches the approved UX mockups in layout, labelling, and navigation. The API endpoints this story depends on are documented in the OpenAPI document and return the documented status codes, including validation failures. Invalid or missing input is rejected at the API with a clear message; no unhandled exception reaches the user. Automated tests cover the happy path and at least one failure path, and the CI pipeline passes. The change is deployed to Dev and verified by the deployment smoke test.
work-item-17 | Task | Design: A safety lead to complete the investigation and close it into a durable reporting record. | A safety lead to complete the investigation and close it into a durable reporting record. | 2 | 4 | agentic-sdlc
work-item-18 | Task | Implement: A safety lead to complete the investigation and close it into a durable reporting record. | A safety lead to complete the investigation and close it into a durable reporting record. | 1 | 12 | agentic-sdlc
work-item-19 | Task | Test: A safety lead to complete the investigation and close it into a durable reporting record. | A safety lead to complete the investigation and close it into a durable reporting record. | 2 | 6 | agentic-sdlc
work-item-20 | Feature | 2. Outcome and release boundary | Tutorial Safety Incident Reporting delivery | 1 |  | agentic-sdlc
work-item-21 | User Story | Clear success and failure feedback, input validation, realistic non-sensitive tutorial data, and automated coverage of the main workflow. | 2. Outcome and release boundary | 2 | 5 | agentic-sdlc | Given the approved requirements for "Clear success and failure feedback, input validation, realistic non-sensitive tutorial data, and automated coverage of the main workflow.", when a business user completes the flow, then the outcome matches the behaviour described in Planning Agent output . The UI screen implementing this story matches the approved UX mockups in layout, labelling, and navigation. The API endpoints this story depends on are documented in the OpenAPI document and return the documented status codes, including validation failures. Invalid or missing input is rejected at the API with a clear message; no unhandled exception reaches the user. Automated tests cover the happy path and at least one failure path, and the CI pipeline passes. The change is deployed to Dev and verified by the deployment smoke test.
work-item-22 | Task | Design: Clear success and failure feedback, input validation, realistic non-sensitive tutorial data, and automated coverage of the main workflow. | Clear success and failure feedback, input validation, realistic non-sensitive tutorial data, and automated coverage of the main workflow. | 2 | 4 | agentic-sdlc
work-item-23 | Task | Implement: Clear success and failure feedback, input validation, realistic non-sensitive tutorial data, and automated coverage of the main workflow. | Clear success and failure feedback, input validation, realistic non-sensitive tutorial data, and automated coverage of the main workflow. | 1 | 12 | agentic-sdlc
work-item-24 | Task | Test: Clear success and failure feedback, input validation, realistic non-sensitive tutorial data, and automated coverage of the main workflow. | Clear success and failure feedback, input validation, realistic non-sensitive tutorial data, and automated coverage of the main workflow. | 2 | 6 | agentic-sdlc
work-item-25 | User Story | Occupational-health case management | 2. Outcome and release boundary | 2 | 5 | agentic-sdlc | Given the approved requirements for "Occupational-health case management", when a administrator completes the flow, then the outcome matches the behaviour described in Planning Agent output . The UI screen implementing this story matches the approved UX mockups in layout, labelling, and navigation. The API endpoints this story depends on are documented in the OpenAPI document and return the documented status codes, including validation failures. Invalid or missing input is rejected at the API with a clear message; no unhandled exception reaches the user. Automated tests cover the happy path and at least one failure path, and the CI pipeline passes. The change is deployed to Dev and verified by the deployment smoke test.
work-item-26 | Task | Design: Occupational-health case management | Occupational-health case management | 2 | 4 | agentic-sdlc
work-item-27 | Task | Implement: Occupational-health case management | Occupational-health case management | 1 | 12 | agentic-sdlc
work-item-28 | Task | Test: Occupational-health case management | Occupational-health case management | 2 | 6 | agentic-sdlc

## 1. Evidence and current stat
Source | Finding
Approved requirements intake | Defines the end-to-end workflow: rapid incident reporting, safety-lead triage and notification, corrective-action tracking through verification, and investigation closure into a statutory-reporting-supporting record.
Project context | Selected stack is Angular + Ionic/TypeScript, FastAPI, and PostgreSQL.
GitHub | Repository csdmichael/tutorial-safety-incident-reporting exists, has main at commit 973a6d2, contains README.md, has no open pull requests, and has no GitHub Actions workflows.
Azure DevOps | Project and an identically named Azure Repos repository exist, but the Azure repo has no branches and the project has no work items.
Intake coverage | Functional requirements are supplied; technical requirements and UX mockups are absent.

## 4. Delivery sequence and dep
Increment | Deliverable | Depends on
1. Foundation | Repository structure, configuration files, database migrations, base UI/API, health checks, seed-data approach, CI validation | Technical decisions below
2. Report | End-to-end incident creation, validation, confirmation, and viewing | Approved report fields and data classification
3. Triage | Triage queue, decisions, and notification records | Role and notification policy
4. Actions | Corrective-action lifecycle and verification | Assignment and verification rules
5. Closure | Investigation closure, immutable lifecycle history, closed record | Closure criteria and reporting-record requirements
6. Hardening | Accessibility/responsive review, automated workflow tests, security review, deployment readiness | All functional increments